## Slide 1: ERP Implementation: A practical Guide
18 June 2024
Notes: Paul + Laura
What is an ERP + why is it important!
How many people in the audience have done an ERP implementation?
Another Slide?

## Slide 2: BIO Paul + Laura
Laura Roversi has 34 years of work experience of which 12 in Project Management. Prior to that, she worked for 22 years in Finance for General Electric, where she held several financial roles. Her first assignments as project manager were SAP ERP integrations and implementations of enterprise standards in Finance. She currently holds the position of IT PMO for the Veolia WTS business unit. She is Project Management Professional certified (PMP). She is currently a Board Member of the PMI Dutch Chapter in the function of Treasurer.
Paul Fagan has 35 years of experience in international banking, manufacturing and logistics. Paul has worked in various operational finance roles for over 13 years. For over two decades he has also focused on Project Management, Program Management and Mergers and Acquisitions. Paul is currently working at CEVA Logistics as a PMO Manager in the Data & Digital – BI & Analytics department. Paul is ACMA and a Project Management Professional (PMP).
Notes: Paul

## Slide 3: What is an ERP and why is it important
Enterprise resource planning (ERP) is usually referred to as a category of business management software—typically a suite of integrated applications—that an organization can use to collect, store, manage and interpret data from many business activities.
Notes: Laura

## Slide 4
SUMMARY
01 Lessons learnt
02 Building a team
03 Governance
04 PLanning & Communication
05 ERP Roadmap Transition
06 Testing - Go-Live - Hypercare - Lessons Learnt
07 Q&A
Notes: Paul

## Slide 5
Generally, we will all encounter that ‘once in a lifetime’ project:
This can be brought about by the need for a
New ERP Implementation.
New financial system.
A merger or divestment.
Take control and make that
‘once in a lifetime experience’
a great one!
Notes: Paul

## Slide 6: HOW TO LEVERAGE PAST EXPERIENCE

## Slide 7: Applying Lessons Learnt
Before starting a new ERP project, it is advisable to retrieve the lessons learnt from previous projects.
Aims:
Avoid previous pitfalls of other similar projects.
Learn from also ‘what worked well’.
Notes: Paul

## Slide 8: Examples & Best Practices Key Lessons Learned Best Practices Local leadership support - a must Standard operating procedures Governance and communications are key Plan, Plan, Plan Training, training, training Training and UAT driven by process maps Rationalize and cleanse data Financial cutover reconciliation (old vs new ERP) Adoption and sustainability To be organization structure available Consider all connected systems Clear requirements
Notes: Laura – Examples of ERP Failures = ABB Brazil ERP failure

## Slide 9: Process Maps
Train
Test
Process Map
Key Strokes
Notes: Laura

## Slide 10: BUILDING A TEAM

## Slide 11: Project Initiation How to build an ERP team
Start with a qualified Project Management Professional internal Project Manager.
Choose an experienced PM with a track record.
Ideally, your PM should be independent of your supplier and/or partners.
Consider an internal PM (if qualified/experienced enough) and/or independent external.
Build a PMO (Project Management Office) team.
The PM needs to manage the workstream leads, supported by the PMO. It depends …
Workstream team with leads
Evaluate internal staffing needs v external staffing needs.
Working with a supplier, use fixed contracts, based on scope of work.
Notes: Larua -
PMO … It Depends Laura - experience / Paul – PMO Experiences. Backfills
Worksteam?

## Slide 12: Workstreams with concrete deliverables
Workstreams are especially used in larger ERP projects to define concrete deliverables per workstream function.
Examples:
R2R : CoA / Account mapping / reports / budget
P2P: workflow / thresholds / aged reporting
O2C: overdues / specification for top 10 reporting
Breaking down a very large project into its component parts by function & ensuring that the right subject matter experts are assigned.
Notes: Paul

## Slide 13: Workstreams Org
Material Mast.- ES
Sourcing/Vendors
Core Team
Local Team Lead
Project Manager
Staff Sponsor
Steering Committee
Integration Core Team
Integration Core GPO’s
Coach/ SME
Customer Services
Material Master ES
Planning, Manu./Inventory
Finance
Projects
Supply Chain
Finance
ITO/OTR
Procurement
Customer Services
To-Be
Accountable
As-Is
Accountable
The Bridge
System Config./Data Conversion/Testing/Training
Responsible
Warehousing/Logistics
Finance
Customer Services
Manufacturing/Warehouse/Logistics
Program Manager
Projects
ITO / OTR
ITO / OTR
A/R
A/P
Tax
Fixed Assets
Treasury
GL & T&E
Intercompany
FPA Reporting
Planning, Manufacturing
Sourcing/Vendors
Sourcing/Vendors
Technical: Internal or external?
Notes: Laura - One Global ERP implies one process\. Examples: attaching invoices / No PO no pay / Localizations.
Paul – Global process owners … Size + Magnitude

## Slide 14: Workstream - Converting to results
RACI : Ensure that you have ‘Workstreams’ with defined roles and responsibilities (R&R) = RACI Model.
WBS : Work breakdown structure (WBS) assigns further to team members deliverables.
Having defined roles and assigned deliverables gives:
Ownership.
Clarity on delivery.
Accountability.
‘Work Stream Leader’ role is to ensure workstream deliverables.
Workstream interdependencies can be identified
Notes: Paul

## Slide 15: Team Development Bruce Tuckman 1965
Role of the PM is to guide project members through each phase of the project lifecycle.
A different management approach is required per phase:
  Forming – utilize informal leaders,
  encourage observers, support new/struggling team members.
  Storming – let ideas flow.
  Norming – concrete deliverables.
  Performing – the goal!
Notes: Paul

## Slide 16: GOVERNANCE

## Slide 17: ERP Project Governance
Project Charter
or
Project Initiation Document (PID)
+ Business Case
Sponsor
Steering Committee
Change Board
(Roles & Responsibilities)
Project Manager + PMO
Workstreams + WBS
Roles & Responsibilities
Project Management Guidelines
Shareholders
Supervisory Board
Managing Board
Units
Articles of Association
Regulations of the Supervisory Board
Charter of the Audit Committee
Charter of the Remuneration Committee
Charter of the Sustainability Committee
Regulations of the Managing Board
Management Framework
Code of Business Conduct
Corporate Requirements & Directives
Corporate Governance: Legal, rules, system, firms are managed + controlled.
Project Governance: Objectives, means to achieve, methodologies, policy + rules.
Notes: Paul Executive sponsorship is a must! Steering committee that represents the business & each workstream Steering committee should be separate to the implementation team ( to maintain the helicopter view).Manage your key stakeholders separately – steeco pre-chats / Timely information - always send your Steeco Pack 48 hours before hand Business case - ensure thta you have a solid business case.

## Slide 18: Governance Translating strategy into deliverables
The PM and/or PMO should ensure:
Meeting cadence to ensure project control and deliverables:
  Defined roles & responsibilities of each body, examples:
  Sponsor : provide funding and overall sponsorship.
  Change Board: guard the scope.
  Steering Committee: decide if the project can pass to the next gate.
  Workstreams: ensure the deliverables.
13 June 2023
Corporate
Governance
Project
Governance
Delivery
Capability
Notes: Paul Tax authorities – want invoicing sequentially / document numbering also in sequence / EDI connections

## Slide 19: PLANNING + COMMUNICATION

## Slide 20: Waterfall Project Processes/Phases
Pre-Project Phase
  Initiation
  Stakeholders
  Resources
  Scope
  Budget
Project Definition and Planning
  Project Plan
  Detailed Plan
  Procurement
  Cost
Execution
  Communication
  Risk
  Quality
Monitor and Control
  Progress
  Change
  Cost
  Time
Closing
  Cost
  Time
  Quality
Start
Communication
End
A Reminder
Notes: Laura ERP projects require a ‘full gate model / waterfall approach’. the overall project is NOT suitable for agile, certain parts maybe.

## Slide 21
Plan, plan + Plan!
Notes: Laura ERP projects require a ‘full gate model / waterfall approach’. the overall project is NOT suitable for agile, certain parts maybe.

## Slide 22: Plan, plan - Plan!
Master ERP Plan
  A single plan that recognizes the interdependencies.
  “A Project Manager should spend 60% of their time planning & the rest communicating”.
  Multiple tools available but you will most likely need:
    An executive summary for sharing with your steering committee and senior stakeholders
    A detailed plan with interdependencies that goes right down to work breakdown structure (WBS).
    Be vigilant as there is a tendency for everyone to maintain their own planning.
    Some large ERP projects have full time planners in the PMO office.
    Ensure that you identify pre-requisites / interdependencies … 1m open items in the sub-ledger
    Plan for Architectural / Landscape needs: a ‘Three Tier Landscape + Parallel Landscape’.
Notes: Paul

## Slide 23
Planning - Communication
  Communication plan
  The key to communication ‘Get the right information to the right people’ the way they want it.
  Communication plan should include both internal and external stakeholders.
  Your Project Manager should practice :
    ‘Active Listening’
    Ladder of inquiry - 7 Whys
    Level 2 communication - See PAiE March Event !
  A multi-media approach, consider a monthly newsletter. … watch out for overload.
  Consider a full time communication or change manager in your team.
  Prepare detailed ‘Black out plan’ for ERP transitions.
  Establish dedicated communication channels for ERP Hypercare.
  Remember, ERP transformation is a journey and you need to involve your users and to guide them through this journey.
Notes: Paul ERP projects require a ‘full gate model / waterfall approach’. the overall project is NOT suitable for agile, certain parts maybe.

## Slide 24: ERP Roadmap Transition

## Slide 25: ERP Roadmap + Change Management
ERP ROADMAP
Discovery phase: “As-IS” to “To-Be” = Plan = Agreed scope.
Minimize customization: (part of business case) + use standard functionality.
Strong ‘Change Board approach’:
  Challenge processes (simplify processes).
  People want to keep ‘as-is’ + extensive change management.
  This can be a Critical success factor.
Use a ‘hard cutover’ with no parallel runs.
Use industry solutions: SAP / Oracle / JDE have solutions per industry.
Commit to ERP enhancements from the minimal viable product to give ‘line of sight’.
Notes: Laura

## Slide 26: ERP Roadmap + Change Management
CHANGE Management
Understand and manage people through the ‘Change Management Lifecycle’ .
Future support Plan the handover to the future ownership model, use roles and responsibilities R&R matrix.
Adoption: the level of adoption can really impact the success of the project. Consider how likely is it that you recommend this system to a colleague.
Promotors: find the promotors, to help others feel psychologically safe.
Celebrate success and the quick wins.
Train your users early on basic navigation, tips and tricks
Train to perform - users need to be trained before UAT starts.
Demo the system and expose your key users to the system and new features
Aim to ‘Satisfy’
Ensure ‘Performance’
‘Happy’ users
Notes: Paul

## Slide 27: TESTING + GO-LIVE + HYPERCARE
Notes: Speaker: Yolanda introduction and hand over to directors

## Slide 28: Testing - Go-Live - Hypercare - Lessons Learnt
TESTING - Before Go-live:
Test, test and test again!
Make a test plan.
Ensure unit, integration, UAT, stress testing, performance testing + evidence.
Plan contingency in your UAT (official UAT time period + 2 weeks).
Confirmed UAT resources.
UAT sign off by Process Owners!!!
ERP Go-live week end(s) and/or Phased Go-Live
Cutover plan.
Freeze periods – shutting down early / no more transactional business.
Golden transactions (production, logistical, EDI, financial etc.)
Monitoring core operational processes.
Check point meetings + Go / no-go with the steering committee + Roll back plan’
Use your accountants - Full reconciliation
  Balance sheet / P&L / Trial Balance / Inventory / Cash
  Before and after!
HYPERCARE
Hypercare – have the team on standby (reactive measures).
Hypercare issue log + Q&A.
Proactive measures – check ins / refresher training sessions can avoid/preempt many challenges.
LESSONS LEARNT
Closing meeting with team + stakeholders.
Finish with lessons learnt!
Notes: Paul

## Slide 29: Q&A

## Slide 30: THANK YOU!